## Sheet1
Work tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
1.1 Requirement analysis
Meet with customers
Identify needs and project constraints
Product statement
Milestone: Product statement defined
1.2 Define design 1
Presentation
Usecase diagram
Review actor
1.3 Define design 2
Userstory card
Activity diagram
Review diagram
1.4 Interface design
System UI idea generate
UI design
Development of UI
Milestone: UI completed
1.5 Code module 1
Define system functionality
Define behavior
Describe models of interaction
Describe grammar check
Review as requird
1.6 Code module 2
Research availability of existing software
Research editing functionality
Research grammer component
Intregrate databage
Intregrate additional component
Milestone: Resuable component indentified
1.7 Management
Isolation software elements
Represent in JIRA
Store in Github
1.8 Integration testing
Prototype
System integration
Evaluate technical checking
Evaluate all function
1.9 System testing
Create a scope definition
Review scope with customer
Revies document as required
Milestone: Testing complete